## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 4 | 3 | 4 | 4*3*4=48 | team leader and all members | 2026-06-16 | Planning ahead as we have not heard from one group member. Have split up roles equally between 3 members. | Have not heard from one group member | closed
| add new team members | One or more team members added to group | 2 | 2 | 2 | 2*2*2= 8 | team leader and all members | 2026-05-14 | Will distribute work load to new member and assign them a leader role. | Waiting untill professor has finalized teams. | closed
| Lack of motivation or responsibility | One or more team member is not participating and finish their tasks on time. | 4 | 4 | 4 | 4*4*4=64 | Team members who are finishing responsibilities. | 2026-06-16 | Weekly meething, check in on progress from everyones responsibility. | Keep team members on team timeline and make sure everyone understand their tasks. | Open
Communication | duplicate work | Two team members working on the same feature. | 1 | 3 | 4 | 1*3*4=12 | Requirement lead | 2026-05-16 | Use GitHub to assign project task and update progress regularly. | Task assigment organized in Github. | Open
| worked on wrong components | Team member is unclear of product requirement. | 3 | 4 | 4 | 3*4*4=48 | team leader and all members | 2026-05-16 | Review requirements together before imitation, planning review for bigger features and weekly meeting check-ins. | Planning review meeting. | Open
| useless work | Team member working on extra feature not apart of product. | 3 | 4 | 4 | 3*4*4=48 | Requirement leader and all members | 2026-05-16 | Planning review and team member progress update. | Weekly team meeting. | Open
| inconsistent work | Team member uses inconsistant coding style causing intigration issues. Not using best coding practices. | 3 | 4 | 4 | 3*4*4=48 | team leader and all members | 2026-05-16 | Code review and creating best practice document. | Consistant code check-in on GitHub. | Open
| Merge conflicts in Git branches | Multiple developers working on React frontend and backend APIs may create merge conflicts. | 3 | 4 | 4 | 48 | Configuration Lead | 2026-06-13 | Use feature branches, enforce pull request reviews, and merge frequently into development branch. | Git branching workflow established in GitHub. | Open
Requirements | unclear requirements | Team member(s) not understanding direction and features added. | 3 | 4 | 4 | 3*4*4=48 | Requirement leader and all members | 2026-05-16 | Clarify assumption, improving the prompt for AI. Clear acceptance criteria for each feature | Weekly check-in with clarification proccess. | Open
| scope creep | [9 empty] | closed
constant requirements changes
| AI-generated hallucinations | AI may generate incorrect or unrealistic test cases not grounded in uploaded product documents. | 4 | 4 | 4 | 64 | QA Lead and AI integration lead | 2026-06-13 | Add retrieval grounding, prompt constraints, and human review before saving generated outputs. | Human-in-the-loop review process planned. | Open
Management | improper task assignments
| improper planning | Not enough team meetings to have everyone on the same page. | 4 | 4 | 4 | 4*4*4=64 | team leader and all members | 2026-05-16 | Team has constant weekly meetings that eveyone can attend.With progress updates. | Weekly meethings for every member to update team with progress. Adjust product timeline if changes are needed. | Open
| lack of management skills | [9 empty] | Open
Technology competence | Not familiar with the framework used | Team member may not have experience with framework being used | 4 | 4 | 4 | 4*4*4=64 |  | 2026-05-16 | Study documentation and divide task according to experience level. | Learning framework | closed
| Not familiar with the programming language used | Team member may not have experience with programming language. (Python or Java) | 4 | 4 | 4 | 4*4*4=64 | All team members | 2026-05-16 | Research coding language and divide task according to experience level. | Asking help from team members and help from AI | closed
Not familiar with unit testing
| Other technology incompetence | Team member does not have experience with AI implementation. | 3 | 3 | 2 | 3*2*2=12 | all team members | 2026-05-16 | Research AI implementation. | Learning how to implement AI feature. | closed
| Not familiar with Git | [9 empty] | closed
Design and implementation | Improper design | System architecture is not efficient. | 4 | 5 | 5 | 4*5*5=100 | Design and implementation lead | 2026-05-16 | Creature architure diagram before implementation is started | Review architure diagram before adding new features. | Open
improper technology stack
| Frontend/backend integration mismatch | React frontend requests may not match Express backend API responses correctly. | 4 | 4 | 4 | 64 | Design and implementation leads | 2026-06-13 | Define API response formats early and test endpoints continuously during development. | API integration testing ongoing | closed
Messy code
Testing | Not enough testing | Generate test cases may contain bugs due to insufficient testing. Not having features ready for testing. | 4 | 5 | 5 | 4*5*5=100 | QA Leader and testers | 2026-05-16 | Preform unit intigration and manual testing integration. | Have feature ready in time for testing. Keep doing functional testing for every feature and don't wait till the end to test. | Open
| Insufficient AI output validation | AI-generated test cases may appear valid but miss important edge cases or business logic. | 5 | 5 | 5 | 125 | QA Leader and testers | 0613/2026 | Create manual review workflow and validate outputs against uploaded product requirements | QA review process currently being designed. | Open
Integration and deployment | Not enough time for integration and deployment | Run out of time and having technical issues. | 4 | 4 | 4 | 4*4*4=64 | Team Leader and Configuration Leader | 2026-05-16 | Set up and test deployment continuously and have enough time for development to solve technical issues | Weekly meeting to stay on product timeline | Open
Schedule | AI generation feature not completed before demo | AI generation workflow may not be fully stable before the scheduled demo. | 5 | 5 | 4 | 100 | Entire Team | 2026-06-13 | Prioritize minimum viable demo functionality and stabilize core workflow before adding optional features. | Current focus is AI generation integration. | Open
Security | Unsafe file upload handling | Uploaded files may contain unsupported formats or malicious content. | 4 | 5 | 4 | 80 | Security Lead | 2026-06-13 | Add file validation, upload restrictions, and secure storage handling. | File validation rules implemented for PDFs. | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.